## Full1
TASK LIST | Team member | Est. Time | Real time | Delivery date (M/D/Y) | TEAM MEMBER | Est. Total Time
Game Introduction module | Gerard | 3h | 8h | 2018-04-14 | Jorge | 20h | 37h
Visco Games module | Nadine, Gerard | 4h | 8h | 2018-04-20 | Nadine | 17h | 30,5h | 0
Insert Coin module | Gerard | 2h | 6h | 2018-04-21 | Martí | 30h | 42h
Players Menu module | Gerard | 4h | 7h | 04/20/18 | Gerard | 33h | 50,5h
Level 01 module | Martí | 1h | 1h | 04/15/18 |  | ?h | ?h
Level 01 scroll, movement, collisions, particles | Martí | 24h | 30h | 04/18/18
Stage Clear module | Gerard | 3h | 5h | 04/17/18
Game Over module | Gerard | 3h | 5h | 04/17/18
Audio module | Jorge | 2h | 3h | 04/15/18
Enemy / enemies module | Nadine | 8h | 18h | 04/22/18
Fade to Black module | Jorge | 1h | 1h 30min | 04/14/18
Input module | All members | 2h | 3h | 04/18/18
Particles module | Nadine, Martí | 4h | 8h | 04/19/18
Render module | All members | 2h | 4h | 04/14/18
Textures module | All members | 2h | 4h | 04/14/18
Player module | Jorge, Gerard | 3h | 4h | 04/19/18
Player 2 module | Jorge | 30min | 1h | 04/20/18
Animation module + animations implemented | All members | 3h | 5h | 04/20/18
Application | Jorge | 1h | 2h | 18/20/18
Fonts module | Jorge | 1h | 5h | 04/21/18
UI module | Jorge | 30min | 1h | 04/20/18
Player weapons | Jorge | 1h | 1h 30min | 04/18/18
Change scenes | All members | 1h | 4h | 04/14/18
God mode | Jorge | 30min | 1h | 04/20/18
Power ups (weapon) | Jorge | 4h | 8h | 04/19/18
Camera limits | Martí | 15min | 30min | 04/18/18
General fixes + bug corrections | All members | 5h | 12h | 04/22/18
Coins logic | Gerard | 1h | 2h | 04/18/18
Score logic | Jorge, Gerard | 1h | 1h | 04/18/18
Stage Clear fix | Jorge | 1h | 3h | 04/20/18
Game Over fix | Nadine | 1h | 2h | 04/20/18