## Full 1
BEFORE ALPHA
TASK LIST | Team member | Est. Time | Real time | Delivery date (M/D/Y) | TEAM MEMBER | Est. Total Time | Real time
Game Introduction module | Gerard | 3h | 8h | 2018-04-14 | Jorge | 20h | 37h
Visco Games module | Nadine, Gerard | 4h | 8h | 2018-04-20 | Nadine | 17h | 30,5h
Insert Coin module | Gerard | 2h | 6h | 2018-04-21 | Martí | 30h | 42h
Players Menu module | Gerard | 4h | 7h | 04/20/18 | Gerard | 33h | 50,5h
Level 01 module | Martí | 1h | 1h | 04/15/18
Level 01 scroll, movement, collisions, particles | Martí | 24h | 30h | 04/18/18
Stage Clear module | Gerard | 3h | 5h | 04/17/18
Game Over module | Gerard | 3h | 5h | 04/17/18
Audio module | Jorge | 2h | 3h | 04/15/18
Enemy / enemies module | Nadine | 8h | 18h | 04/22/18
Fade to Black module | Jorge | 1h | 1h 30min | 04/14/18
Input module | All members | 2h | 3h | 04/18/18
Particles module | Nadine, Martí | 4h | 8h | 04/19/18
Render module | All members | 2h | 4h | 04/14/18
Textures module | All members | 2h | 4h | 04/14/18
Player module | Jorge, Gerard | 3h | 4h | 04/19/18
Player 2 module | Jorge | 30min | 1h | 04/20/18
Animation module + animations implemented | All members | 3h | 5h | 04/20/18
Application | Jorge | 1h | 2h | 18/20/18
Fonts module | Jorge | 1h | 5h | 04/21/18
UI module | Jorge | 30min | 1h | 04/20/18
Player weapons | Jorge | 1h | 1h 30min | 04/18/18
Change scenes | All members | 1h | 4h | 04/14/18
God mode | Jorge | 30min | 1h | 04/20/18
Power ups (weapon) | Jorge | 4h | 8h | 04/19/18
Camera limits | Martí | 15min | 30min | 04/18/18
General fixes + bug corrections | All members | 5h | 12h | 04/22/18
Coins logic | Gerard | 1h | 2h | 04/18/18
Score logic | Jorge, Gerard | 1h | 1h | 04/18/18
Stage Clear fix | Jorge | 1h | 3h | 04/20/18
Game Over fix | Nadine | 1h | 2h | 04/20/18
Enemies implementation + in-game | Gerard, Jorge, Nadine | 10h |  | 2018-01-06
UI (lifes player 1) + continue | Jorge
Fix bullet colliders | Jorge
Player 1 == Player 2 | Gerard | 4h | 8h | 05/17/18
Game Over and Neo Geo fixed | Gerard | 2h | 2h | 05/14/18
Full screen ratio corrected | Martí
Layout level 3 | Martí
Fix spaceship animation | Jorge, Gerard | 2h | 2h | 05/26/18
All UI (including player 2) | Gerard | 6h | 7h | 05/27/18
Bullets delay | Jorge
Gamepad | Gerard | 2h | 5h | 05/20/18
Fix Visco Games | Jorge
Weapon Power Ups | Gerard, Jorge | 6h | 8h | 05/19/18
Power up mechanism | Nadine, Jorge
Control mapping | Gerard | 1h | 1h 30min | 05/22/18
Map colliders | Martí
General bug fixes | All members | 6h |  | 2018-01-06
Andro Dunos video + web | Gerard | 1h |  | 2018-01-06
Player 2 spawn in-game | Gerard | 30 min | 1h | 05/27/18
Fix controllers | Gerard | 30min | 45min | 05/23/18
AFTER ALPHA
VERSION | TASKS |  |  |  |  | IN CHARGE | ESTIMATED TIME | REAL TIME
0.6 | -Fix game over / neo geo / visco games |  |  |  |  | Gerard/"Jorge" | 4h | G: 3h J: 30 min
| -Fix all current bugs |  |  |  |  | ALL | 5h | J: 2h G: 1h M: 1h
| -Fix spaceship turbo |  |  |  |  | Nadine | 6h | 30min
| -Añadir dos disparos restantes hasta el power up 2 de la nave |  |  |  |  | Jorge/Gerard | 3h | J: 1h G: 1h
| -Enemy power-up fully implemented |  |  |  |  | Nadine/Jorge | 10h | N: 22h20min J:5h
| -Fix shot colliders + its power-ups |  |  |  |  | Martí/"Jorge" | 1h | M: 30min without success J: 3h 45min
| -Controller |  |  |  |  | Gerard | 2h | 4h
| -UI (lifes + Continue) |  |  |  |  | Jorge | 1h 30min | 5h 30 min
| -Update controls + debug controls |  |  |  |  | Nadine | 30min | 25min
0.7 | -Background + Layout without moviment vertical without colliders. |  |  |  |  | Martí | 8h | 19h 30min
| -player 1 == player 2 (fully implemented) |  |  |  |  | Gerard | 4h | 6h
| -Finish all weapon power-ups.(colliders correctly, only shots, power Up new module) |  |  |  |  | Jorge/Gerard | 10h | J: 5h G: 5h
| -Finish UI(including both players score) |  |  |  |  | Gerard | 2h | 3h
0.8 | -Layout with vertical movement |  |  |  |  | Martí | 1h | 1h
| -All special attack. |  |  |  |  | (excluded)
| -Add rockets, shields..(power-up bonus animation, etc)(adding power-ups). |  |  |  |  | (excluded)
| -//1/2 enemies (20-27) |  |  |  |  | Jorge/Gerard/Martí | 4h | G: 4h M: 1h 30 min
0.9 | -All enemies |  |  |  |  | Gerard/Jorge | 4h | G: 5h
-Power-up sum (extras).
| -Colliders level 3 |  |  |  |  | Martí | 4h | 4h 30 min
| -1/2 Boss(first phase). |  |  |  |  | Martí | 5h | 7h 50min
1.0 | -2/2 Boss (all).
| -Enemy HP |  |  |  |  | Gerard | 30min | 45min
| -TESTING |  |  |  |  | All | 30min | 30min
| -README and BUILD NICE |  |  |  |  | Gerard | 10min | 15min
[6 empty] | TEAM MEMBER | Est. Total Time | Real time
[6 empty] | Jorge | 3h 30min
Nadine
[6 empty] | Martí | 23h | 36h 20 min
[6 empty] | Gerard | 26h | 33h 30min